## Slide 1
Work package 2
NA2: HARMONISATION OF POLICIES, BEST PRACTICES, TRAINING AND SUPPORT
Ana Casino, SYNTHESYS+ WP2 Leader
www.synthesys.info

## Slide 2: Summary of WP aims + objectives
Coordination in policy development processes; Harmonisation of policy implementation actions and the Support activities, including training and helpdesk.
CREATE implementation guidance for policies
DISSEMINATE best practices and standard operating procedures
PROVIDE helpdesk support resources
IDENTIFY trining programmes to expand digital workforce skills
SHARE online resources on prioritised management topics

## Slide 3: Progress on WP tasks
Task 2.2 (M1-18)
Task 2.3 (M1-24)
Task 2.4 (M19-46)
Integrate & expand collection assessments
Develop focused training activities
Helpdesk for online support
PP1: analysis of ICEDIG D2.2
PP1: Collation of training activities
Follow-up with JRA1 for technical specifications
PP3: fine-tuning of Dashboard matrix with test partners (BGM, HNHM and RBINS)
Task 2.1 (M1-45)
Harmonization of policies
PP1: analysis of ICEDIG D7.2
PP3: Survey distributed among partners
PP2: identification of areas (3) and policy groups (17)
PP2: definition of categories and group classifications
PP2: Analysis of ICEDIG D8.1 (Recommendations)
PP5: translation into visual graphs (via BI)
PP3: Gaps and duplications analysis
PP4 Analyses of survey results from partners
PP4: development and dissemination of survey to obtain collection data from partners (deadline:18th May).
PP4 : Contact WP leaders (2nd half of March) to ensure all DiSSCo training areas are covered
PP6: Coordination with DEST for Transferring procedures
PP5: Capturing training material for filling in detected gaps

## Slide 4: Progress on Work Package Deliverables
Deliverable D2.1 (M45)
Deliverable D2.2 (M18)
Deliverable D2.3 (M24)
Basic Manual for policy implementation
Joint Dashboard of Collections
Catalogue of Training Modules
PP2: Compilation of responses and categorization of results (priority areas, criteria for classification, parameters for harmonization, guidelines for adoption)
PP1: Experts session for defining technical structure, basic criteria and design – (MS25-M6): CETAF Brussels 23 July 2019
PP1: Workshop on training resources and programme definition: landscape analysis, modules interface, integration into DEST - (MS26-M12): MNHN Paris, 23 Jan 2020
PP1: (MS23-M8): online survey distributed among project partners, on existing policies, best practices and standards
PP3: Collaboration with DEST as to identify procedures and methodology for enabling training modules transfer
PP2: Interaction and dialogue with JRA1 and TDWG to follow technical specifications
PP3: Alignment with ISTC wg
Next MS24-M32: Workshop for integration
PP4: Interaction with ESWG for specific integration of earth sciences collections

## Slide 5: Dissemination Progress + Plans
Dashboards-visual tool for representing high-level info
BIODIVERSITY_NEXT Conference
Leiden, NL, 21-25 October 2019
Workshop on training needs and prioritization
MNHN Paris, 22-23 February 2020
Training School on digitization and DM challenges for small collections
MOBILISE TS
Warsaw, PL, 13-14 February 2020

## Slide 6
Current major detected risks for the smooth development of NA2:
T2.1
  Variety of policies and diversity on the actors needed to collate documentation (scattered across departments at each institution)
  Dependencies on other WPs developments
  T2.2
  Classification and harmonisation of terms:
  a) Unique identifiers for collections/institutions
  b) Reference to MIDS levels (still improving)
  Alignment needed with TDWG and other developments under CETAF ISTC wg
  Delays in providing data to survey (CSIC and MfN have requested 1 month delay)
T2.3
Definition on the level of development of training material (no budget for new material)
Capturing material for the missing topics
Promotion of usage of material
T2.4
Task not started yet
Risks and issues incl. COVID-19

## Slide 7
Apart from the normal difficulty of collating information across a variety of actors and the effort needed to unify and harmonize it, there are some specific risks to highlight:
  Variety of policies and protocols across institutions and countries, and the diversity of implementation level and the capacity to further endorse those
  Lack of agreed terms (for e.g. MIDS, Collections identifiers)
  Dependencies on other WPs developments
Mitigation measures are being put in place as to strengthen coordination, keep focus activities and ensure getting timely and useful feedback from partners:
Organization and participation in meetings with related WPs and WGs
Reminders and support to keep partners committed to facilitating requested info
Follow-up closely the developments achieved by others in standards and terminology
The COVID-19 pandemic has already have some identified effects on NA2:
    Possible furloughs in certain partners that may delay hiring process of dedicated people
    Overloads of work on several partners’ representatives
    Difficulties in managing due response to requests for feedback
Risks and issues incl. COVID-19

## Slide 8: Meetings and stakeholders
Planned meetings
- Dashboard team meetings every month (12th May)
- Connection to JRA1 weekly meetings
Key stakeholders
- Partners:
T2.1: NHMW, RBINS, BGM, MfN, CSIC, MNHN, HNHM, RBGE, RBGK
T2.2: NHM, RBINS, BGM, MfN, UCPH, CSIC, MNHN, HNHM, Naturalis
T2.3: MNHN, RBINS, NHMW, RMCA, MfN, HNHM, NRM, UGOT-GGBC, RBGK
T2.4: Naturalis, RMCA, MNHN
- External stakeholders: DEST, TDWG, GBIF
- Complementary initiatives: MOBILISE, DiSSCo Prepare (WP2 and WP7)

## Slide 9
Any questions?
www.synthesys.info