## Slide 1
Work package 7
JRA2: Collections on Demand
www.synthesys.info
Eva Chatzinikolaou WP7 leader
Patricia Mergen (7.1), Jonathan Brecko (7.2), Pete Hollingsworth (7.3)

## Slide 2: Summary of WP aims + objectives
Requests for Collection on Demand
Develop a workflow to support requests for Virtual Access to collections
Establish Digitisation on Demand for collections as a service
Develop routine laboratory protocols and workflows for DNA sequencing from Natural History collections

## Slide 3: Progress on WP tasks
Task 1
Task 2
Task 3
Digitisation as a Service model
Developing processes and pipelines for high resolution imaging services, including 3D models of NH specimens: Digitisation on Demand
Developing the protocol infrastructure for DNA Sequencing on Demand
Support Virtual Access calls
Develop cost models (MS56 - done)
Optimisation of DNA extraction protocols from preserved specimens: protocols research and lab work commenced
Optimisation and refinement of sequencing protocols from preserved specimens: protocols research and lab work commenced
Standardisation of techniques and outcomes
Follow up current VA call (MS53 in progress)
Liaise with DiSSCo Prepare WP4 on cost model
Improvement of digitization techniques (reduce time and costs)
Storage of VA calls data

## Slide 4: Progress on Work Package Deliverables
Del 1
Del 2
Del 3
D.7.1 Paper on the implementation, assessment and sustainability business plan of VA (Month 40 – May 2022)
Data pipelines + standard workflows, enabling online access to complex digital content (3D scans) (Month 30 – July 2021)
Publication providing synthesis of cost effective + scalable workflows for NH collections DNA sequencing (Month 44 – Sept 2022)
Improve digitization techniques
Currently optimisation of protocols for DNA extraction and sequencing from preserved specimens is in progress.
Monitoring VA call 1 (MS53 Month 22) to feed into call 2
Follow up on JRA1 Elvis implementation for VA
Linking with DiSSCo Prepare WP4 (cost models)
Linking with EOSC (business plan and cost models )
Reduce human and computational time (e.g. use Deep Learning for mCT-scans segmentation)
Reduce costs by developing protocols to efficiently use free software (e.g. LHpFusionBox, Dragonfly, GOM Inspect, MeshLab, etc.)
Literature will be reviewed and integrated with project findings to develop a scientific publication

## Slide 5: Dissemination Progress + Plans
Joint paper on VA Ideas call
published in RIO – January 2020
Planned publications
Publication on implementation, assessments and sustainability business plan of VA (Del 7.1 – M40)
Scientific publication on new data pipelines and standard workflows (MS58-M36)
Publication on synthesis of cost effective + scalable workflows for NH collections DNA sequencing (Del 7.3 – M44)

## Slide 6
General issues
Challenging to assess costs and feasibility of requests (Task 7.1)
Requests are slower to come in than were the ideas (Task 7.1)
Delays due to Covid-19 situation
Staff is not able to physically inspect the collections to check feasibility of the requests (Task 7.1)
Delays in follow up of VA call 1 and suggestion of recommendations for future calls (Task 7.1)
Delays on development of pipelines for improving computational time and advancing software best practices. Staff needs to get fully functional remote access to the powerful institutional workstations (by using TeamViewer licenses) (Task 7.2)
Delays in optimisation of DNA protocols (Task 7.3) because active laboratory work is completely suspended. Timelines will be revised during the following weeks and we are confident the work can be completed on time.
Risks and issues incl. COVID-19

## Slide 7: Meetings and stakeholders
Participation to the following meetings has been planned:
1) Biodiversity Information Standards (TDWG)
2) Society for Preservation of Natural History Collections (SPNHC)
3) Meetings of COST Mobilise, CETAF and DiSSCo
***Due to Covit-19 planned meetings are postponed or will take place virtually
Key stakeholders
Scientific experts (including those participating in the VA evaluation panel), laboratory scientists, specimen curators
Universities and Research institutes
Museums and Private sector

## Slide 8
Any questions?
www.synthesys.info