## Slide 1
Work Package 10 - Virtual Access (VA)
Sandy Knapp, Access Stream Coordinator
www.synthesys.info

## Slide 2: WP10 – what is Virtual Access in SYNTHESYS+?
VA (WP10) will be covered by a single work package, offering user-driven Collections on Demand services to specimens at 19 collection-holding beneficiaries.
VA will enable Users to identify priority specimens and/or collections for digitisation with data deposited and annotated in internationally recognised repositories operating FAIR practices
DoD requests will be submitted by users to host institutions to agree feasibility of digitisation Spring 2020
Requests will be prioritised by an external panel. Data will be delivered through openly accessible public data portals, and tracked to demonstrate impact (registered in ELViS, JRA1)

## Slide 3: Summary of VA (WP10) aims + objectives
Trial of digitisation-on-demand for NH collections
Ideas Call - November 2019
First Call – Spring 2020
Second Call – Spring 2021

## Slide 4: VA (WP10) Programme Summary (1)
VA is not the same as TA – a VA request comes not from an individual, but from a community
A single VA request can be for material from several different institutions
Funds for VA go to the digitising institution – NOT to the requester
VA in SYNTHESYS+ means request for collections data in digital form
  Digital images
  Digital data
  Digital molecular or chemical data
Requesters must contact the VA Coordinator well in advance of any call deadline

## Slide 5: VA (WP10) Programme Summary (2)
19 SYNTHESYS+ partners participating in VA
Available facilities are adapted from the information on the TA part of the website, and from previous ICE-DIG documents
Ideas Call was run as a test case in October-November 2019
  Hardy et al. 2020. Research Ideas and Outcomes 6: e50354, doi: 10.3897/rio.6.e50354
First Call opened February 2020; closes ???
Requests will be prioritised by a Prioritisation Panel when Call closes
  Panel members: André Heughebaert, Christo Arvantidis, Carol Butler, Niki Keklikoglou, Lene Krøl Andersen, Nina Rønsted, Nick Harris (SK to chair, non-voting)

## Slide 6: 2019 Ideas Call (WP10)
Ideas Call to test community interest and our own processes was run October-November 2019
Received 26 completed requests (more ideas were discussed with VA Coordinators, but did not result in completed requests)
  Digitising institutions range – 1 to 13
  Requester number range – 1-15 people
  Wide range of collection types
Requesters did not receive individual feedback, but generalised feedback provided in report published in RIO (Hardy et al. 2020. Research Ideas and Outcomes 6: e50354, doi: 10.3897/rio.6.e50354)

## Slide 7: 2019 Ideas Call (WP10)
Some of the general feedback:
  VA Coordinator contact essential
  Requests must have benefit to research community
  Not limited to European requesters
  Address wider societal challenges
  Need to demonstrate (not just name) wider support
  Balance coverage with feasibility
  Provide evidence to support statements
  Write request for a general audience (Panel)
  All data generated must be open and FAIR; make use of existing data portals (own institutions or aggregators like GBIF, Genbank etc.)
  Costs are challenging – allocated on demand basis
  VA Coordinators can say NO to requests that are not feasible

## Slide 8: VA (WP10) Progress to date (1)
Coordinators in place at each participating institution
  Tasks are to coordinate between requesters of VA and curators in their institution (also to provide costings to enable requesters to refine proposals
  VA Coordinators not necessarily the person same as TA Coordinators
Ideas Call was run successfully
ELViS (JRA 1) is being developed to handle VA requests – several iterations; Access+ELViS meetings will be regular to handle teething problems
Requests are being received by VA Coordinators at most participating institutions (18 of 19)

## Slide 9: VA (WP10) Progress to date (2)
Deadline for requesters to contact VA Coordinators was put back to 30 April (purpose of deadline was to alleviate last-minute rush of requests that are more complex than TA – institutions can still accept requests!)
Requests to date cover a range of collections; several involve more than one VA institution
  Invasive species of Oxalis – several institutions
Only some have been entered into the ELViS platform – majority in development still
ELViS functionality for VA being worked on at speed
COVID19 has affected the programme (more later)

## Slide 10: Progress on VA (WP10) Milestones and Deliverables
Milestone (MS71) – the first VA Call
D10.1 - Assessment of VA by external board
Call 1 for VA launched
In addition to the Prioritisation Panel the VA Programme will be assessed by a Panel of external experts
30th of April – deadline for contacting VA Coordinators (will have better idea of the number of active requests)
Composition of this board currently being discussed; membership will be decided on in due course and invitations will go out
VA Coordinators working with requesters to refine proposals

## Slide 11: Dissemination Progress + Plans WP10
VA (and SYNTHESYS+) in social media
Re-tweets greatly appreciated!
Published report from the Ideas Call
Hardy et al. 2020. Research Ideas and Outcomes 6: e50354, doi: 10.3897/rio.6.e50354
Biodiversity Next -
Leiden Oct 2019
Presentation in the DiSSCo Symposium about the SYNTHESYS+ approach to VA
[Text]
[Text]
REPLACE SQUARES WITH LEADING IMAGES

## Slide 12
Risks for the VA Programme (WP 10)
  Communications around what Virtual Access actually is, and how to define digitisation on demand
  How to reach those who would benefit from VA beyond our own community?
Current issues and risks
    Complete readiness of ELViS system for seamless handling of VA requests
    Due to current COVID19 restrictions some curators are unable to access collections in order to provide completely accurate estimates for costings
Risks and issues incl. COVID-19

## Slide 13: Meetings and stakeholders – VA (WP10)
Quarterly meetings of all VA Coordinators (also attended by others from their institutions)
  Last one held on 23 April 2020
Regular meetings ELViS+Access to streamline feedback
Key stakeholders
  JRA1 – development of ELViS for VA deployment is an important test case for its use more broadly
  ELViS users – feedback from VA Call will help drive improvements
  JRA2 – molecular and 3D data provision models
  VA participants – will benefit from digitised collection data!

## Slide 14
Any questions?
www.synthesys.info