## Slide 1
Work package 5
NA5: Internationalisation and engagement of new user communities in EC priority areas
Tim Robertson
NA5 Coordinator, GBIF Secretariat
www.synthesys.info

## Slide 2: Summary of WP aims + objectives
Integrate with international stakeholders to develop the global collections research agenda
Roadmaps for infrastructure component areas
Expand geographic coverage
Alignment and coordination with major EU stakeholders

## Slide 3: Progress on NA5 tasks Decisions from MS43, the all-hands virtual workshop, July 2019
T5.2 - MfN
T5.3 - CETAF
T5.4 - Naturalis
Expanding geographic involvement
Engaging society and industry as users of our RI
European biodiversity infrastructures stakeholder forum
MS43 agreement was to adopted a two-phase approach
T5.1 - GBIF
Three workshops focusing on
Integrating collections descriptions into a collections catalogue
Workshop 1 running now as a virtual workshop
Integrating services relating to citation and use tracking
Integrating specimen related data
Implementation roadmaps for infrastructure component areas
Workshop 2 recently cancelled
Ideas paper
Global consultation
Roadmap report, and report on virtual workshop process
MS43 identified South East Asia, Eastern Europe and Balkan nations
Small grant awards (€5k) for networking, training, digitization and sharing (e.g. GBIF)
Call closed April 2020, now under review*
June 2020 – Jan 2022, projects executed
* Latest information. Coronavirus may have delayed
Invite experts in two workshops to advise the process (March 2020)
Approach selected companies proposing small engagement projects (Q3 2020)
Building on work on GBIF Spain Node
Assessment of landscape and opportunities: opt to focus on Risk Assessment and Technology companies
Refocussed: Establish a sustainable communication channel with the European Environmental Agency (EEA), as one of the relevant EU data-driven policy bodies for the RI perspective.
MS45 First alignment workshop with partners and 3 external experts
D5.4 Whitepaper on aligning activities and services targeting the EEA through the Catalogue of Life as an integration point for collections-based data.

## Slide 4: Progress on Work Package Deliverables
D5.4
Whitepaper on opportunities for increased alignment with other EU infrastructures
Originally due Jan 2020, anticipated September 2020
Connect species data curated by the EEA with species data curated in the collections-based RI DiSSCo?
Topics:
Define the science / policy interface between species data RIs and Science Policy infrastructures
Exemplify how collection-based data curated in DiSSCo (occurrence, DNA sequences, traits) can be used in legal reporting of the EEA by hypothetical use cases

## Slide 5: Dissemination: Task 5.2 & T5.3
Task 5.2 open call available on Synthesys+ website
  Communicated through existing network and GBIF Participant Node channels
Task 5.3 plan to prepare a leaflet / bulletin advertising the T5.3 task and the benefits for industries to get involved

## Slide 6: Dissemination: Task 5.1
Building on the Alliance for Biodiversity community
Communicated through Alliance, TDWG, GBIF, DiSSco mailing lists and associated Twitter
General process
  Ideas paper drafted by core team
  Dedicated forum established
  Moderated daily with summaries in multiple languages
Plan to produce a report on output and a report on lessons from running the virtual workshop

## Slide 7
Sense there are high demands on staff time; difficult to arrange meetings, slow or lacking responses to emails (externally and internally); acknowledge that little resources dedicated to the tasks and be realistic.
Deliverable D5.4 due Jan 2020 delayed; anticipated September 2020
  Rationale: Scope change, delayed meetings, new task lead March 2020
Building active engagement using virtual workshops both an opportunity to broaden engagement and a risk that few contribute; strong focus on these aspects, including multiple languages. Will review and report on process within Task 5.1
Coronavirus pandemic:
  T5.1: The 2nd workshop scheduled for SPNCH Conference now cancelled. Will reconsider approach following review of first virtual workshop
  T5.3: Expect industry engagement meetings need to be virtual
Risks and issues incl. COVID-19

## Slide 8: Meetings and stakeholders
Planned and recent meetings
  T5.1: Virtual workshop 1 now underway
  T5.3: To be planned: Meetings with industry partners
  T5.4: Online Catalogue of Life+, European Environment Agency and GBIF meetings held, and subsequent discussion ongoing
Key stakeholders (beyond DiSSCo project involvement)
GBIF node community (e.g. GBIF Spain, iDigBio, Atlas Living Australia)
Index Herbariorum
Catalogue of Life
Biodiversity Information Standards (TDWG)
European Environment Agency
Alliance for Biodiversity

## Slide 9
Any questions?
www.synthesys.info