## Slide 1
Work package 6
JRA1: Optimisation of Access
Wouter Addink, Naturalis
www.synthesys.info

## Slide 2: Summary of WP aims + objectives
Primary objective: to develop ELViS the unified European Loans and Visits System, a DiSSCo e-Service
To unify access requests to all specimens in collections in Europe
To integrate a live data dashboard reporting on collections data and access
To deliver improved management on loans and for digitisation on demand workflows

## Slide 3: Progress on WP 6 tasks
Task 6.1
Task 6.2
Task 6.3
System architecture design of The ELViS system
ELViS components development
Testing and integration of workflows
Lead: Naturalis
Lead: Picturae
Lead: NRM
MS47 completed: Workshop for ELViS System design
MS50 completed: Temporary system in place for VA registration
MS52 delayed: Workflow integration workshop (cause: Covid-19)
In progress: Incremental development of ELViS as open source software based on the designs from task 6.1, experimenting with CORDRA as core part of the Digital Object Architecture, delivery of functionality for TA and VA processes (workflows described in T7.1) in month 24
In progress: design built on DSarchitecture and recommendations developed in ICEDIG
MS48 completed: AAI infrastructure design
In progress: Incremental testing of the ELViS developed components
In progress: specification of requirements for local systems (CMS, loan administration) to be compatible with ELViS in the future: survey created to investigate current systems and collection management workflows in use.

## Slide 4: Work Package 6 Deliverables (1)
D 6.1
D 6.2
D 6.3
Inventory and Analysis of Dataflows
Piloting Access through an AAI infrastructure
ELViS Helpdesk
Report (public)
Demonstrator (public)
Report (public)
Due: M39 (29 April 2022)
Due: M24 (Jan 2021)
Due: M18 (31 July 2020)
MS48 ready (AAI infrastructure design)
on hold – waiting for delayed workshop
Functionality discussed in 2019 workshop,
planned for implementation in Q3-4 2020.
Pilot planned for 2021

## Slide 5: Work Package 6 Deliverables (2)
D 6.4
D 6.5
D 6.6
ELViS System for Unified Access
Specification and requirements for integration with ELViS
Results of pilot workflow integrations with ELViS Report (public)
Report (public)
Due: M42 (31-1-2022)
Due: M39 (2-5-2022)
Demonstrator (public)
Due: M42 (1-8-2022)
Implementation in progress: first version of VA implemented, admin functions in progress, mockups for TA implementation created, data for institutes, collections, facilities under discussion
Survey created
Pilots planned for 2021

## Slide 6: Dissemination Plans
ELViS Integration Specification distributed to CMS and loan administration providers
ELViS unified access service online & registered in service catalogs
Results of pilot integrations
publication
Presentations in partner networks and international meetings,
social media

## Slide 7
Risks and issues
Probability
Severity
Not sustainable
Insufficient quality
Not compatible with DiSSCo Core Architecture
Too late for
VA programme
Integration with NA2 dashboard fails
No uptake in DiSSCo after Synthesys+
Align With ICEDIG & DiSSCo Prepare WP5,6
Align with other WPs MOBILISE, stakeholders
Mitigation:
Added value, Usability, DiSSCo governance

## Slide 8
ELViS workflow integration workshop in Task 6.3, MS52 prepared for early April but delayed due to COVID-10 outbreak. Now planned for early October.
Dependencies:
D6.1: Inventory and Analysis of Dataflows report, lead Naturalis, to be ready in July 2020.
ELViS developments towards v1 (VA and TA workflows implemented).
No other major dependencies, as the pilots can be carried out next year.
Mitigation:
Discuss the survey outcomes online, so we can still create this in draft in July. That will give enough material to avoid delay in the further ELViS developments towards v1 (VA and TA workflows implemented).
However finishing the deliverable is not really possible until after the workshop has being held. Need to postpone the deliverable D6.1.
New risk: COVID-19

## Slide 9: Meetings & stakeholders
Planned meetings:
  Workflow integration workshop (MS52), month ?
  Weekly JRA1 meetings
  Alignment meetings with e.g. VA/TA coordination, CETAF, GBIF
  Picturae development team meetings
Key stakeholders
  WP6 partners: Naturalis, Picturae, NRM, NHM, MNHN, GRNET, MfN, NHMW, RMCA, BGM, CETAF, NMP, SGN, CSIC, LUOMUS, HCMR, HUJI, TDWG, RBGE
  TA and VA Facilities
  DiSSCo partners, scientists, industry, RDA, TDWG, GBIF, CoL, CETAF

## Slide 10
Any questions?
www.synthesys.info