## Slide 1: Risks: COVID-19
Risk / Issue | Mitigation
Project staff unavailable / overloaded / recruitment delays | Use deputies where available. Delay timetable.
Meetings / workshops / conferences cancelled | Present virtually if possible. Increase social media use.
Knock-on effects / WP dependencies | Examine Gantt chart & alert task leaders / WP leaders of risks.
Collections / laboratories / infrastructure closed or inaccessible | Delay timetable.