## Slide 1
Work package 4
NA4: Digital Standards & Processes
Quentin Groom, Meise Botanic Garden & TDWG
Anton Güntsch, Botanischer Garten und Botanisches Museum Berlin-Dahlem
Roger Hyam, Royal Botanic Garden Edinburgh
www.synthesys.info

## Slide 2: Summary of WP aims + objectives
Fully interoperable collection data across Europe
Increase standards compliance
Linked Open Data capabilities
CETAF Stable Identifiers adoption
IIIF rollout

## Slide 3: Progress on WP
4.1 Standards
4.1 Standards
4.2 Linked Data
  Biodiversity data standards: landscape analysis and compliance
Adoption and development of the CETAF stable identifier framework
  Collection Description Task Group (https://github.com/tdwg/cd/)
  Attribution Task Group (https://www.tdwg.org/community/attribution/)
Extended use at different levels.
Setup and documentation of a machine-readable open CETAF Identifier Catalogue
Continuous semantic enrichment
Biodiversity data standards: landscape analysis and compliance
Bioschemas (https://bioschemas.org/)
Minimal Information for Digital Specimens (MIDS)

## Slide 4: Progress on WP
4.2 Linked Data
4.3 IIIF
Adoption and development of the CETAF stable identifier framework
International Image Interoperability Framework (IIIF)
Enhancement of IIIF endpoint at RBGE (https://iiif.rbge.org.uk/)
Establishment of IIIF endpoints to JACQ network of herbaria (https://www.jacq.org)
Establishment of IIIF endpoints at Meise Botanic Garden
Under discussion at Paris and Kew
Re-implemented PHP redirection scripts for specimen identifiers
Revised documentation of CETAF ID standards on the BioWikiFarm
Co-ordinated planning of ID-related developments with all 4.2 partners

## Slide 5: Progress on Work Package Deliverables
Progress made on developing and extending standards
Implementation manual for IIIF and CETAF Identifiers in the NH collections
  A paper submitted titled “People are essential to linking biodiversity data”
Documentation on stable identifiers has been consolidated and pooled.
Gradual development of the IIIF documentation.
A guide of best practices documentation
Openly available at https://cetafidentifiers.biowikifarm.net
Continuously add relevant specifications as they become available.
  Numerous online meetings
Due Month 18
  Due month 40
Continued development of demonstration application as spin off from British Council funded project (https://youtu.be/_4DuNBVsWW8)
Due Month 24
  Standards Compliance Dashboard

## Slide 6: Dissemination Progress + Plans
Mobilise Wikidata Workshop
A workshop to investigate the use of Wikidata and Wikibase in biodiversity informatics
Biodiversity Next
Person attribution
Semantic Annotation
Wikimedia
etc
CETAF DWG/ISTC
Vienna 2019
Virtually in 2020
Collection Description
A TDWG Interest & Task Group
Led by Deb Paul & Matt Woodburn

## Slide 7
What are the major risks to your WP?
  Balancing the spending of time across the whole project
  Availability of non-Synthesys partners
Are there any current issues?
  Furloughed staff at three partner institutions.
Has the current coronavirus pandemic already affected your WP, and if so, how?
  No immediate impacts, but it depends on how long restrictions go on.
Risks and issues incl. COVID-19

## Slide 8: Meetings and stakeholders
Meetings at SPNHC and the Biodiversity Summit have been cancelled, but substitutes are being considered
Stakeholders at collections everywhere

## Slide 9
Any questions?
www.synthesys.info