## Slide 1
Work package 1
NA1: Management
Kristina Gorman, SYNTHESYS Project Manager
Annual General Meeting, 28-29th April 2020
www.synthesys.info

## Slide 2: NA1: Management
Management responsibilities
NHM Management Team contacts
Risks update including COVID-19
EC Project Officer communications
Month 12 spend update
Month 18 reporting AUGUST 2020
Project Council business: GA amendment
NA1 deliverables + milestones update

## Slide 3: NA1: Management responsibilities
NHMMT (NHM Management Team): Project coordinator, project manager & project support; weekly/fortnightly meetings; communications, admin, risk monitoring, events & dissemination
PC (Project Council): Project coordinator, stream coordinators, WP leaders & TAF leaders; 6-monthly teleconferences; ensure integration of 3 streams (JRA, NA & Access)
EB (Executive Board): Project coordinator & stream coordinators; 3-monthly teleconferences; Oversee activities across all WPs

## Slide 4
NHM Management Team
Vince Smith | Project Coordinator | v.smith@nhm.ac.uk | +44 207 942 5127 | 
Kristina Gorman | Project Manager | k.gorman@nhm.ac.uk | +44 207 942 5816 | Part-time
Scott Wilson | Project Support | Scott.wilson@nhm.ac.uk | +44 207 942 5849 | 
Helen Harling | Project Support | h.harling@nhm.ac.uk | +44 207 942 5840 | Project Manager support January20 – June20
Daniel O’Donnell | Project Support | synthesys@nhm.ac.uk |  | 
synthesys@nhm.ac.uk |  | 1st point of contact for admin and Access queries |  | 

## Slide 5: Risk management
Maintaining & updating project risk register
Planning mitigation measures
Working with WP leaders to identify & manage risks
Reduce likelihood of risks becoming issues
Key risks on Teamwork
All identified risks on risk register (project deliverable, updated every 6 months)
During this meeting: new risks (in particular linked to COVID-19) and their mitigation measures to be collated, presented at the end of the meeting, and added to risk register

## Slide 6: Risk management: COVID-19
Main risks:
Project members unable to work due to illness, care responsibilities, place of work circumstances (e.g. furloughing, unable to access workplace resources)
Stakeholders not able to engage in project activities (e.g. Access users not able to apply to TA/VA programme, delegates not able to attend workshops/meetings)
Impacts:
Delays to, or failure to meet milestones & deliverables
Low quality outputs / low levels of uptake & engagement with outputs
Mitigation:
Increased use of teleconference facilities & virtual meetings
Increased communications (consortium & externally)
Adjusted timeline & deadlines

## Slide 7: Risk management: COVID-19
Main risks:
Project members unable to work
Stakeholders not able to engage in project activities
Short-term: unable to access collections (major impact on TA & VA in particular), laboratories (affecting e.g. DNA protocols work) & infrastructure (e.g. computational & software)
Slow-down in pace of work
Delays cause knock-on effects (e.g. VA Call)
Dependencies between WPs
Recruitment delays
Dissemination: unable to travel attend meetings to disseminate project work & results

## Slide 8: EC Project Officer communications
Current GA amendment (Teklia to replace A2iA)
COVID-19 impact: EC Project Officer aware of current & expected delays
  Article 51 (Force majeure):
    to justify delays, cancellation of activities
    formal notification to the Commission, take steps to limit any damage.
  Each beneficiary should keep record of the correspondence relating to the cancellation and impossibility of reimbursement. You will need to save emails relating to these cancellations (following article 18: beneficiaries must keep records and other documentation for a period of 5 years after the payment of the balance).
  No current plans to invoke Article 51, but request for any foreseen delays to deliverables or milestones to be communicated to WP Leaders & synthesys@nhm.ac.uk

## Slide 9: Spend update
M12 financial spend update per WP
On- or under-budget in all WPs.
Summary M12 reports per WP to be shared with WP Leaders & requested to take action on areas not on budget.
Chart: 
| Time | NA1 | NA2 | NA3 | NA4 | NA5 | JRA1 | JRA2 | JRA3 | TA1 | VA1
 | 12 | 159280.7763 | 177780.3419 | 75394.9362 | 134826.4054 | 106043.7875 | 268053.3542 | 47546.7459 | 67276.3971 | 640814.7074 | 23888.7215
 | 36 | 544613.0837 | 322119.5081 | 479585.6038 | 464736.0746 | 394780.9125 | 782338.9058 | 592321.2241 | 586306.2229 | 3159185.2926 | 973106.9985

## Slide 10: Spend update
M12 financial spend update per beneficiary
Most are under-budget
If spend is more or less than expected according to work plan, beneficiaries requested to justify deviation.
Chart: 
| NHM | NHMW | RBINS | RMCA | BGM | CETAF | NMP | BGBM | MfN | SGN | SMNS | ZFMK | UCPH | GBIF | CSIC | LUOMUS | MNHN | HCMR | GRNET | HNHM | HUJI | Naturalis | Picturae | TDWG | NRM | UGOT-GGBC | RBGE | RBGK | Digirati | UNIMAN-BioVel | Teklia
 | 333826.7562 | 103300.9125 | 34608.9867 | 31203.1606 | 107274.0813 | 60194.025 | 20791.25 | 42054.515 | 64171.0625 | 0 | 37219.5125 | 39089.5669 | 49687.21 | 55212.5 | 68139.165 | 105677.0125 | 162113.2 | 9366.325 | 8595.6875 | 31176.0937 | 23462.25 | 122248.9125 | 120203.3 | 0 | 707 | 11493.8051 | 42479.3568 | 21457.0202 | 2216.25 | 5159.125 | 0
 | 1249022.3938 | 316763.9875 | 297527.6733 | 227377.9594 | 207537.8087 | 142747.945 | 183453.56 | 201380.715 | 392455.0575 | 278800.43 | 90650.4475 | 221279.8531 | 313158.78 | 128427.28 | 253855.685 | 385483.9675 | 556389.78 | 72852.425 | 117904.3125 | 149872.1663 | 192620.18 | 609725.0375 | 292248.95 | 7812.5 | 416971.43 | 53744.0149 | 471191.1432 | 193285.3498 | 39033.75 | 160133.495 | 63163.88

## Slide 11: Reporting requirements
1st periodic report, covering 1st February 2019 – 30th July 2020
Deadline to Coordinator: 31st August 2020
Deadline to EC: 30th September 2020
Financial report: financial statement from each beneficiary
Technical report:
Part A: publishable summary, economic and social impact
Part B: explanation of work carried out.
Overview of work, results, summary of deliverables & milestones
Objectives: work towards achievement of each objective
Explanation of work carried out, giving details of work carried out by each beneficiary.
Impact of work: is section 2.1 of DoA still relevant or need updating?

## Slide 12
Mid-Term Review
MTR requirements:
Update to EC Project Officer on project progress
Planned to be Oct/Nov 2020 following submission of 1st periodic reports
WP leaders to present progress reports

## Slide 13: Project Council business
Risk register: updates / amendments
GA amendment (number 1 – current)
  Minor clarifications required by EC Officer
For Project Council discussion:
  WP10 (VA): Beneficiary 12 (ZFMK Bonn) request to join WP
  Possible changes to deliverables and milestones deadlines

## Slide 14: NA1 Deliverables & Milestones
Deliverables to date:
Meetings: KOM, AGM1
Risk management: 6-monthly risk register updates
Data Management Plan
Milestones to date:
Project Council 6-monthly teleconferences
Executive Board 3-monthly teleconferences

## Slide 15
Any questions?
www.synthesys.info